## Estimating & Budget Worksheet
BUDGETING / Draw Schedual and Time line
Category / Draw Item | SUBCONTRACTOR/CONTRACTOR'S Item Description | ESTIMATED COST |  |  |  | ACTUAL COST | VARIANCE | CURRENT PAID | AMOUNT DUE
|  | LABOR | MATERIALS | EQUIPMENT | TOTAL
Draw 1 @ MONTH 1
1000-3 Temp Power |  | 9000 |  |  | 9000 |  |  |  | 0
1000-4 Dumpster |  |  |  | 7500 | 7500 |  |  |  | 0
1000-6 Temp Toilet |  |  |  | 4000 | 4000 |  |  |  | 0
1000-7 Architectural Fees | Interior Designer | 12500 |  |  | 12500 |  |  |  | 0
1000-9 Building Permits |  |  | 41500 |  | 41500 |  |  |  | 0
1000-12 Survey/Drawings/Plans |  | 5000 |  |  | 5000 |  |  |  | 0
1000-13 General Contractor | Consulting during Design-Design-Development & Deposit for Construction (20%) | 22000 |  |  | 22000 |  |  |  | 0
1000-14 Expenses | Initial Draw for HOA Dues, Insurance & Utility Payments |  | 10000 |  | 10000 |  |  |  | 0
3000-1 Grading | Grading, drainage & retention per grading plan | 23000 |  | 5500 | 28500 |  |  |  | 0
7000-5 Rough Plumbing | Underground plumbing | 4000 | 4500 |  | 8500 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Subtotal |  | 75500 | 56000 | 17000 | 148500 | 0 | 0 | 0 | 0
Draw 2 @ MONTH 2
7000-12 Rough Electrical | Underground electrical | 3000 | 3000 |  | 6000 |  |  |  | 0
4000-4 Foundation | Foundation, footings, excavation | 19000 | 16000 | 8000 | 43000 |  |  |  | 0
5000-1 Framing | Lumber, Hardware & Labor - Per Framing Contract (progress payment) | 40000 | 45000 | 5000 | 90000 |  |  |  | 0
1000-13 General Contractor | Progress Payment (monthly) | 10000 |  |  | 10000 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Subtotal |  | 72000 | 64000 | 13000 | 149000 | 0 | 0 | 0 | 0
Draw 3 @ MONTH 3
5000-1 Framing | Lumber, Hardware & Labor - Per Framing Contract (progress payment) | 32000 | 40000 | 2000 | 74000 |  |  |  | 0
5000-3 Roof Trusses | Per approved plans |  | 19000 |  | 19000 |  |  |  | 0
5000-5 Windows | Windows ordered - Per Window Contract (progress payment) |  | 46500 |  | 46500 |  |  |  | 0
1000-13 General Contractor | Progress Payment (monthly) | 10000 |  |  | 10000 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Subtotal |  | 42000 | 105500 | 2000 | 149500 | 0 | 0 | 0 | 0
Draw 4 @ MONTH 4 - WEEK 2
5000-3 Roof Trusses | Per approved plans - Final Payment |  | 6000 |  | 6000 |  |  |  | 0
5000-5 Windows | Windows delivered & installed - Per Window Contract (progress payment) |  | 46500 |  | 46500 |  |  |  | 0
6000-1 Roofing | Foam Roof per approved plans - Per Roofing Contract |  | 29500 |  | 29500 |  |  |  | 0
7000-5 Rough Plumbing | Rough Plumbing per plans - Per Pluming Contract (progress payment) | 8000 | 8000 |  | 16000 |  |  |  | 0
7000-12 Rough Electrical | Rough Electrical per plans - Per Electrical Contract (progress payment) | 5000 | 9000 |  | 14000 |  |  |  | 0
7000-16 HVAC | Rough HVAC per plans - Per HVAC Contract (progress payment) | 10000 | 10000 |  | 20000 |  |  |  | 0
Subtotal |  | 23000 | 109000 | 0 | 132000 | 0 | 0 | 0 | 0
Draw 5 @ MONTH 4 - WEEK 4
3000-16 Fencing | Parameter Walls | 4000 | 4000 |  | 8000 |  |  |  | 0
3000-18 Pool / Spa | Pool / Spa - Per Pool Contract (digging, concrete) (progress payment) | 20000 | 15000 |  | 35000 |  |  |  | 0
7000-9 Fire Sprinkler | Rough Fire Sprinkler per plans - Per Fire Sprinkler Contract (progress payment) |  | 6000 |  | 6000 |  |  |  | 0
7000-19 Home Automation | Per Contract - Pre-wire throughout (progress payment) | 3000 | 2000 |  | 5000 |  |  |  | 0
7000-20 Home Entertainment System | Per Contract - Pre-wire throughout (progress payment) | 3000 | 2000 |  | 5000 |  |  |  | 0
7000-21 Home Security System | Per Contract - Pre-wire throughout | 1000 | 500 |  | 1500 |  |  |  | 0
8000-1 Fireplace | Fireplace linear (LR) installed |  | 6500 |  | 6500 |  |  |  | 0
1000-7 Architectural Fees | Interior Designer | 12500 |  |  | 12500 |  |  |  | 0
1000-13 General Contractor | Progress Payment (monthly) | 10000 |  |  | 10000 |  |  |  | 0
1000-14 Expenses | Draw for HOA Dues, Insurance & Utility Payments |  | 10000 |  | 10000 |  |  |  | 0
12000-5 Construction Contingency | Contingency (allocated for “Structural” building phase) |  | 15000 |  | 15000 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Subtotal |  | 53500 | 61000 | 0 | 114500 | 0 | 0 | 0 | 0
Draw 6 @ MONTH 5
7000-5 Rough Plumbing | Rough Plumbing per plans - Per Pluming Contract (progress payment) | 3000 | 4000 |  | 7000 |  |  |  | 0
7000-9 Fire Sprinkler | Rough Fire Sprinkler per plans - Per Fire Sprinkler Contract (progress payment) |  | 2000 |  | 2000 |  |  |  | 0
7000-12 Rough Electrical | Rough Electrical per plans - Per Electrical Contract (progress payment) | 3000 | 3000 |  | 6000 |  |  |  | 0
7000-16 HVAC | Rough HVAC per plans - Per HVAC Contract (progress payment) | 6000 | 6000 |  | 12000 |  |  |  | 0
9000-2 Interior Doors | Doorframes installed - Doors on site (progress payment) |  | 11000 |  | 11000 |  |  |  | 0
8000-3 Insulation | Insulation throughout |  | 9500 |  | 9500 |  |  |  | 0
8000-4 Drywall | Drywall - Per Drywall Contract (hanging) (progress payment) | 4000 | 14000 |  | 18000 |  |  |  | 0
6000-5 Exterior Stucco | Per Stucco Contract - Wrapping (progress payment) | 10000 | 10000 |  | 20000 |  |  |  | 0
1000-13 General Contractor | Progress Payment (monthly) | 10000 |  |  | 10000 |  |  |  | 0
12000-5 Construction Contingency | Contingency (allocated for “Structural” building phase) |  | 15000 |  | 15000 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Subtotal |  | 36000 | 74500 | 0 | 110500 | 0 | 0 | 0 | 0
Draw 7 @ MONTH 6
8000-4 Drywall | Drywall - Per Drywall Contract (taping, texture) (progress payment) | 6000 | 4000 |  | 10000
10000-7 Trim/Baseboard | Baseboard installed throughout |  | 3000 |  | 3000
10000-8 Tile for Bathrooms | Showers & Wet Areas - Shower prep-work (progress payment) | 3000 | 2500 |  | 5500
6000-5 Exterior Stucco | Per Stucco Contract - Stucco Finish (progress payment) | 7000 | 7000 |  | 14000
6000-13 Exterior Veneer | Per Designer Specification, Accent Walls |  | 8000 |  | 8000
6000-15 Exterior Paint | Exterior Paint throughout per Designer Spec | 5000 | 3500 |  | 8500
9000-8 Cabinets | Cabinetry throughout in production (progress payment) | 5000 | 18500 |  | 23500
6000-9 Deck | Flatwork throughout - Per Concrete Contract (progress payment) | 7000 | 7000 |  | 14000
12000-4 Miscellaneous Items | Allowance per Designer Spec |  | 10000 |  | 10000
1000-13 General Contractor | Progress Payment (monthly) | 10000 |  |  | 10000
Subtotal |  | 43000 | 63500 | 0 | 106500 | 0 | 0 | 0 | 0
Draw 8 @ MONTH 7
9000-8 Cabinets | Cabinetry delivered & installed (progress payment) | 5000 | 5000 |  | 10000 |  |  |  | 0
8000-6 Interior Paint | Paint throughout - Prime Interior Walls (progress payment) | 3000 | 2000 |  | 5000 |  |  |  | 0
10000-1 Tile | Flooring for BA & Wet Areas - Material on site |  | 5000 |  | 5000 |  |  |  | 0
10000-3 Wood Flooring | Material on Site - Prep-Work - Install (progress payment) | 2500 | 15000 |  | 17500 |  |  |  | 0
10000-8 Tile for Bathrooms | Showers & Wet Areas - Tile Installation (progress payment) | 2500 | 2700 |  | 5200 |  |  |  | 0
10000-9 Installation / Labor |  |  | 9000 |  | 9000 |  |  |  | 0
6000-9 Deck | Flatwork throughout - Per Concrete Contract (progress payment) | 6000 | 7000 |  | 13000 |  |  |  | 0
3000-20 Exterior Firepit | Firepit instlled |  | 4000 |  | 4000 |  |  |  | 0
3000-21 Exterior BBQ | BBQ Installed (build structure, equipment) | 2000 | 3500 |  | 5500 |  |  |  | 0
3000-8 Landscape | Landscaping throughout - Plants & Irrigation installed (progress payment) | 6000 | 8000 |  | 14000 |  |  |  | 0
1000-13 General Contractor | Progress Payment (monthly) | 10000 |  |  | 10000
12000-5 Construction Contingency | Contingency (allocated for “Finish” building phase) |  | 10000 |  | 10000
Subtotal |  | 37000 | 71200 | 0 | 108200 | 0 | 0 | 0 | 0
Draw 9 @ MONTH 8
9000-2 Interior Doors | Doors installed (progress payment) |  | 3000 |  | 3000 |  |  |  | 0
8000-6 Interior Paint | Paint throughout - Paint Interior Walls (progress payment) | 1000 | 2000 |  | 3000 |  |  |  | 0
9000-8 Cabinets | Cabinetry doors & hardware (progress payment) | 1000 | 4000 |  | 5000 |  |  |  | 0
9000-9 Countertops | Countertops throughout - fabricated & installed | 8000 | 8000 |  | 16000 |  |  |  | 0
11000-6 Appliances | Appliance Package - delivered & installed |  | 24000 |  | 24000 |  |  |  | 0
10000-3 Wood Flooring | Material on Site - Prep-Work - Install (progress payment) | 5000 |  |  | 5000 |  |  |  | 0
3000-8 Landscape | Landscaping throughout - Surface delivered & installed (progress payment) | 6000 | 8000 |  | 14000 |  |  |  | 0
3000-18 Pool / Spa | Pool / Spa - Per Pool Contract (equipment, finish) (progress payment) | 15000 | 10000 |  | 25000 |  |  |  | 0
3000-22 Exterior Gates | Gates Installed |  | 2500 |  | 2500 |  |  |  | 0
6000-6 Garage Doors | Delivered & Installed |  | 5500 |  | 5500 |  |  |  | 0
1000-13 General Contractor | Progress Payment (monthly) | 10000 |  |  | 10000 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Subtotal |  | 46000 | 67000 | 0 | 113000 | 0 | 0 | 0 | 0
Draw 10 @ FINAL
7000-7 Plumbing Fixtures | Delivered & Installed |  | 10000 |  | 10000 |  |  |  | 0
7000-14 Electrical Fixtures | Delivered & Installed |  | 5000 |  | 5000 |  |  |  | 0
10000-11 Garage Floor | Garage finished floor | 1000 | 1200 |  | 2200 |  |  |  | 0
9000-5 Mirrors | Mirrors (frameless) installed |  | 2200 |  | 2200 |  |  |  | 0
9000-6 Shower Doors | Frameless enclosure installed |  | 2700 |  | 2700 |  |  |  | 0
7000-19 Home Automation | Per Contract - Components delivered & installed (progress payment) | 1000 | 4000 |  | 5000 |  |  |  | 0
7000-20 Home Entertainment System | Per Contract - Components delivered & installed (progress payment) | 2000 | 5000 |  | 7000 |  |  |  | 0
1000-13 General Contractor | Progress Payment (monthly) | 10000 |  |  | 10000 |  |  |  | 0
1000-14 Expenses | Initial Draw for HOA Dues, Insurance & Utility Payments |  | 5000 |  | 5000 |  |  |  | 0
12000-1 Exterior Clean-Up | Final Cleanup | 3000 |  |  | 3000 |  |  |  | 0
12000-2 Interior Cleaning | Interior Cleaning | 1500 |  |  | 1500 |  |  |  | 0
12000-3 Staging | Staging & Artwork - Furnished throughout |  | 35000 |  | 35000 |  |  |  | 0
1000-13 General Contractor | Progress Payment (monthly) | 8000 |  |  | 8000 |  |  |  | 0
12000-5 Construction Contingency | Contingency (partial draw as needed for Final Items & Punch-List) |  | 10000 |  | 10000 |  |  |  | 0
Subtotal |  | 26500 | 80100 | 0 | 106600 | 0 | 0 | 0 | 0
Draw 11 @ N/A
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Draw 12 @ N/A
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
[5 empty] | 0 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Enter Additonal Items Here |  |  |  |  | 0 |  |  |  | 0
Subtotal |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL CONSTRUCTION COSTS |  | 454500 | 751800 | 32000 | 1238300 | 0 | 0 | 0 | 0
\