## Construction Budget
Construction Budget Submission Form
Lay out the details of your project here.
Version | 4.3
Step 1: Fill out a description of the entire construction project. |  | Scope of Work: |  | Start Date: | 2019-05-27
|  | Modern luxury estate ground up construction. The lot is one of the last available vacant building lots in a private gated luxury home community called Villaggio at Frank Sinatra. The subject property is centrally located in a primier target area for luxury home buyers. Finished property will be a 3,950sf modern home with 4BR, 4.5BA, Den/Office, Pool/Spa, 3-Car Garage |  | Estimated Completion Date: | 2020-03-15
|  |  |  | Expected Draws: | 10
[5 empty] | Current | Projected
|  |  |  | Total Square Feet: | 0 | 3950
|  |  |  | Rooms/Units: | 0 | 1
Total: | 1238300 |  |  | Bedrooms: | 0 | 4
|  |  |  | Bathrooms: | 0 | 4.5
|  |  |  | Kitchens: | 0 | 1
Step 2: Fill in each line item with the description of the construction cost, the amount, the estimated date of completion, and the draw item name (if necessary).
Item Number | Category / Draw Item | Description | Amount | Estimated Completion Date
Soft Costs
Column1 | Column2 | Column3 | Column4 | Column5
1000-2 | Temp Gas* | (Enter your description here)
1000-3 | Temp Power* | supplied by Socal Edison | 9000
1000-4 | Temp Dumpster |  | 7500
1000-6 | Temp Toilet | supplied by Burrtec | 4000
1000-7 | Architecutral Fees | incl designer fee | 25000
1000-8 | Engineering Fees |  | 0
1000-9 | Building Permit* | incl permit fees & school fees | 41500
1000-10 | Impact Fees
1000-12 | Survey/Drawings/Plans* |  | 5000
1000-13 | General Contractor | GC Fee | 110000
1000-14 | Expenses | Insurance, Property Taxes, HOA Fees | 25000
1000-15 | (Enter your line item here)
1000-16 | (Enter your line item here)
| Total Soft Costs |  | 227000
Demolition- Trashout
2000-1 | Demolition*
2000-2 | Trashout
2000-3 | Dumpster
2000-4 | 0 |  | 0
| Total Trashout |  | 0
Yard- Landscape
3000-1 | Grading* | Grading, drainage & retention per gading contract | 28500
3000-3 | Underground *
3000-4 | Conduit
3000-5 | Water Lines*
3000-6 | Septic * | n/a
3000-7 | Sewer Lines*
3000-8 | Landscape | Landscpaing throughout incl. material & labor | 28000
3000-9 | Fence
3000-10 | Concrete
3000-11 | Asphalt
3000-12 | Pavers-Hardscape
3000-13 | Deck
3000-14 | Sod-Plants
3000-15 | Rock
3000-16 | Fencing | Parameter walls | 8000
3000-17 | Sidewalks
3000-18 | Pool | Pool, Spa, equipment & installation | 60000
3000-19 | Spa | included in pool contract | 0
3000-20 | Exterior Firepit | exterior firepit per approved plan, linear layout | 4000
3000-21 | Exterior BBQ | exterior bbq per approved plan, | 5500
3000-22 | Exterior Gates | steel frame, glass insert | 2500
3000-23 | (Enter your line item here)
3000-24 | (Enter your line item here)
3000-25 | (Enter your line item here)
3000-26 | (Enter your line item here)
3000-27 | (Enter your line item here)
| Total Yard-Landscape |  | 136500
Foundation
4000-1 | Footings* | included in foundation contract | 0
4000-2 | PreTreat | included in foundation contract | 0
4000-3 | Foundation - Post Tension Cables | n/a | 0
4000-4 | Foundation * | Foundation, footings, excavation | 43000
4000-5 | Excavation* | included in foundation contract | 0
4000-6 | Pour | included in foundation contract | 0
4000-7 | Repair | n/a | 0
4000-8 | (Enter your line item here)
4000-9 | (Enter your line item here)
4000-10 | (Enter your line item here)
| Total Foundation |  | 43000
Structure
5000-1 | Framing * | Lumber, Hardware & Labor | 164000
5000-3 | Roof Trusses | per approved plans | 25000
5000-4 | Windows |  | 93000
5000-5 | Window Installation | included in window contract 5000-4 | 0
5000-7 | Joist System
5000-9 | (Enter your line item here)
5000-10 | (Enter your line item here)
5000-11 | (Enter your line item here)
5000-12 | (Enter your line item here)
| Total Structure |  | 282000
Exterior
6000-1 | Roofing* | Foam Roof per approved plans | 29500
6000-2 | Flashing | included in roofing contract 6000-1 | 0
6000-3 | Siding
6000-5 | Stucco | fine spray grade, smooth elements where applicable | 34000
6000-6 | Garage Door | plat panel, insulated | 5500
6000-7 | Gutters | n/a | 0
6000-8 | Solar
6000-9 | Deck | Flatwork throuhout | 27000
6000-11 | Driveway
6000-13 | Masonry Veneer | per designer specification | 8000
6000-15 | Painting - Exterior | per designer specification, including accent walls | 8500
6000-16 | Front & side porch
6000-17 | (Enter your line item here)
6000-18 | (Enter your line item here)
6000-19 | (Enter your line item here)
6000-20 | (Enter your line item here)
6000-21 | (Enter your line item here)
6000-22 | (Enter your line item here)
6000-23 | (Enter your line item here)
| Total Exterior |  | 112500
Systems
7000-1 | Rough HVAC* | (Enter your description here)
7000-2 | Trim HVAC
7000-3 | Final HVAC
7000-4 | Underslab Plumbing
7000-5 | Rough Plumbing* | Plumbing throuhgout incl underground and rough | 31500
7000-6 | Trim Plumbing
7000-7 | Plumbing - Fixtures | per designer specification | 10000
7000-8 | Finish Plumbing
7000-9 | Fire Sprinklers Rough | per approved plans | 8000
7000-10 | Fire Sprinklers Trim
7000-11 | Underslab Electrical
7000-12 | Rough Electrical* | Electrical throughout incl rough and finish | 26000
7000-13 | Trim Electrical
7000-14 | Electrical Fixtures | per designer specification | 5000
7000-15 | Finish Electrical
7000-16 | HVAC Total | HVAC contract incl rough-ins, parts & labor | 32000
7000-19 | Home Automation | Automated lighting system, keypads, etc | 10000
7000-20 | Home Entertainment System | Speakers, Controls, etc | 12000
7000-21 | Home Security System | pre-wired | 1500
7000-22 | (Enter your line item here)
| Total Systems |  | 136000
Interior
8000-1 | Fireplace | Linear fireplace w remote control | 6500
8000-2 | Fireplace Surround
8000-3 | Insulation | Insulation througout | 9500
8000-4 | Drywall* | smooth finish throughout | 28000
8000-5 | Tape-Texture
8000-6 | Paint-Interior | Color scheme per designer spec. incl. accent colors | 8000
8000-7 | Lighting
8000-9 | (Enter your line item here)
8000-10 | (Enter your line item here)
8000-11 | (Enter your line item here)
8000-12 | (Enter your line item here)
8000-13 | (Enter your line item here)
| Total Interior |  | 52000
Finishes
9000-1 | Finish Carpentry - base, shelving | (Enter your description here)
9000-2 | Interior Doors | Paint-grade doors, prehung | 14000
9000-3 | Finish Hardware
9000-4 | Exterior Doors
9000-5 | Mirrors | frameless, per designer specificaiton | 2200
9000-6 | Shower Doors | shower enclosures, no doors | 2700
9000-7 | Accessories- Towel bars, TP MC
9000-8 | Cabinets | Custom Cabinets throughout | 38500
9000-9 | Countertops | Countertops per designer specification | 16000
9000-10 | Crown Molding
9000-11 | (Enter your line item here)
9000-12 | (Enter your line item here)
9000-13 | (Enter your line item here)
9000-14 | (Enter your line item here)
9000-15 | (Enter your line item here)
9000-16 | (Enter your line item here)
9000-17 | (Enter your line item here)
| Total Finishes |  | 73400
Flooring
10000-1 | Tile | tile flooring in bath rooms & wet areas | 5000
10000-2 | Marble
10000-3 | Wood Flooring | engineered hardwood flooring in main and bed rooms | 22500
10000-4 | Carpet
10000-5 | Vinyl
10000-7 | Trim/Baseboard | per designer specification | 3000
10000-8 | Tile for bathroom, walls, floors | per designer specification | 10700
10000-9 | Installation / Labor | Labor & Material for installation | 9000
10000-10 | Garage Floor | finished flooring per designer specification | 2200
10000-11 | (Enter your line item here)
| Total Flooring |  | 52400
Appliances
11000-1 | Range | (Enter your description here)
11000-2 | Cooktop
11000-3 | Microwave
11000-4 | Dishwasher
11000-5 | Refrigerator
11000-6 | Package | Appliance Package Thermador & secondary brands | 24000
11000-7 | Gas Appliances*
11000-8 | (Enter your line item here)
| Total Appliances |  | 24000
Final - Misc
12000-1 | Exterior Clean-up | Final Clean-up | 3000
12000-2 | Interior Cleaning | Final Clean-up | 1500
12000-3 | Staging | Staging & Artwork | 35000
12000-4 | Miscellaneous Items | Allowance for additional items per designer spec | 10000
12000-5 | Construction Contingency |  | 50000
12000-6 | (Enter your line item here)
12000-7 | (Enter your line item here)
12000-8 | (Enter your line item here)
12000-9 | (Enter your line item here)
| Total Misc. |  | 99500
*THESE ITEMS REQUIRE PERMITS IN MOST JURISDICTIONS. BORROWERS ARE REQUIRED TO ADHERE TO ALL LOCAL LAWS, CODES, REGULATIONS AND REQUIREMENTS AS EXPRESSED IN YOUR LOAN DOCUMENTS.

## Glossary
Construction Budget Glossary
Definitions for budget categories
ITEM | DEFINITION
Appliances | installed appliances
Cabinets | installed kitchen and bath, etc.
Demo* | demolition and removal of structure interior or exterior
Driveway | installation or repair
Drywall | installation, tape, mud, sand
Electric Service* | connection to local power grid and/or solar installation
Electrical- Finish | lights, fixtures, switched, receptacles, etc.
Environmental | mold and lead remediation, etc.
Exterior | enclosure, wrapping and finish
Flooring | installed flooring
Foundation* | installation of, addition to or repairs to existing
Framing* | new interior structure- walls, ceilings, stairs, etc.
Garage | construction of or repair to structure (roofing in 7.0)
HVAC* | installation or repair of heating air conditioning, ducts
Insulation | installation of new insulation, air-sealing, etc.
Landscaping | adjacent to building only
Other | BE SPECIFIC
Other Finishes
Paint | primer and paint complete with all trim
Plans* | professionally prepared and signed drawings and/or plans
Plumbing- Finish | sinks, faucets, toilets and connections
Roof* | decking, covering, flashing, gutters, ventilation and skylights
Rough Electrical* | installation of new wire, panel (in or behind walls)
Rough Plumbing* | installation feed lines, drain/waste, vents and tub
Site* | lot preparation- clearing and rough grading
Water/Sewer* | connection to public services. well and/or septic work
Windows* | installation or new or repairs
*Permits may be required from government agencies with jurisdiction or authority. It is the borrowers responsibility to obtain all relevant permits. Documentation will be required with draw requests.